# Production Scheduling & Tracking Requirements

| Sr. No. | Area | Requirement / Action Item | Responsibility | Remarks |
| --- | --- | --- | --- | --- |
| 1 | Activity Tracking | Add Planned Date against every activity in the production schedule. | Prem | Establish baseline schedule |
| 2 | Activity Tracking | Add Actual Date against every activity completed. | Prem / Concerned Owner | Track execution status |
| 3 | Activity Tracking | Add Variance (+/- Days) column. | Prem | Identify delays and accelerations |
| 4 | Supplier Tracking | Record PO Release Date for each purchased item. | Purchase Team | Track procurement status |
| 5 | Supplier Tracking | Record Supplier Committed Delivery Date. | Purchase Team | Based on supplier commitment |
| 6 | Supplier Tracking | Record Actual Delivery Date. | Stores / Purchase | Monitor supplier performance |
| 7 | Supplier Tracking | Record Delay / Advancement (+/- Days). | Prem / Purchase Team | Supplier scorecard basis |
| 8 | Supplier Performance | Review historical supplier lead times and delivery performance. | Prem, Surinder, Rakesh, Akshay, Sanoj | Create realistic schedules |
| 9 | Team Coordination | Conduct review meeting with key team members. | Prem | Validate planning assumptions |
| 10 | Material Availability | Verify whether POs are released for all BOM items. | Prem / Purchase Team | Before fabrication planning |
| 11 | Material Availability | Review status of critical materials and long lead items. | Prem / Purchase Team | Prevent production delays |
| 12 | Shop Floor Review | Discuss material shortages and bottlenecks with Sanoj. | Prem | Align with actual conditions |
| 13 | BOM Management | Review complete BOM for each project. | Prem / Planning Team | Ensure all items covered |
| 14 | Production Planning | Schedule fabrication only after confirming material availability. | Prem / Production Team | Avoid idle resources |
| 15 | Progress Monitoring | Track Planned Progress vs Actual Progress. | Prem | Weekly review |
| 16 | Delay Analysis | Record reasons for delay against each activity. | Concerned Department | Root cause analysis |
| 17 | Corrective Action | Define corrective actions for delayed activities. | Prem / Team Leaders | Recovery planning |
| 18 | Delivery Planning | Prioritize jobs that can be dispatched within the current month. | Prem | Improve invoicing |
| 19 | Cash Flow Alignment | Align production priorities with invoicing and cash flow requirements. | Prem / Management | Business critical |
| 20 | Monthly Review | Review schedule adherence and supplier performance monthly. | Prem / Management Team | Continuous improvement |
| 21 | Overall Objective | Integrate Procurement, Supplier Tracking, Material Availability and Production Scheduling into one system. | Prem | End-to-end visibility |

## Recommended Excel Tracking Format

| Project | Activity | Responsibility | Planned Date | Actual Date | Variance (+/- Days) | Material Available (Y/N) | PO Released (Y/N) | Supplier Name | Supplier Committed Date | Actual Supply Date | Delay (+/- Days) | Status | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |