## 24.04.2026
Production Schedule : 11.06.2026
Sr.No. | Customer Name | PO. NO. & Date | Delivery Date | Dispatch Date | Status
1 | Priyanjas - Container Systems | PJ/YWSPL/020-R1/25-26 DTD : 10.06.2025 | 10-12 Week
| Laminar setllar 2 nos & Storge Tank : 2 Nos |  |  |  | Fabrication Done & Painting & Leakge test pending
| Container Body |  |  |  | Waiting for further clearance
2 | JSW Dolvi - 12K SLN - 01 Nos | 4700157911, dtd : 10.12.2025 |  | 13.06.2026 | Ready for Dispatch
3 | JSPL Angul 3 Mtr - Vessel Systems | 4561180787, dtd : 07.02.2026 |  | 18.06.2026
| Media Filter |  |  |  | Under Painting
Manifold
| Valve |  |  |  | Recived
| Compressor |  |  |  | Received
| Panel |  |  |  | Received
| Fastners |  |  |  | on date 12.06.2026 will recive
| Media & Gravers |  |  |  | on date 12.06.206 will recive
| Lateral |  |  |  | on date 15.06.2026 will recive
| Backwash Pump |  |  |  | on date 13.06.206 will recive
| Lateral Header Pipe |  |  |  | on date 13.06.206 Will ready
4 | Rashmi Metal - 18K - 02 Nos | 30.03.2026 |  | 12.06.2026
| Screen |  |  |  | on date 11.06.2026 will recive
| FAT |  |  |  | on date 11.06.2026 will recive
5 | Ion Exchange 18K - 2 nos | 4100011453, Dtd : 19.04.2026 |  | 25.06.2026
| Document Approval |  |  |  | Recived
| Material Receive |  |  |  | Recived
| Machining |  |  |  | One set is reday only painting & assembly pending Housing material will recive on 13.06.2026
| Fabrication Housing |  |  |  | 17.06.2026 machining will done (SR Engg Work)
| Hydro |  |  |  | 21.06.2026
| Blasting Paintng |  |  |  | 24.06.2026
| Assembly |  |  |  | 25.06.2026
| FAT |  |  |  | 25.06.2026
6 | Thermax - 7.2K 03 Nos |  | 12-16 week for approval | 26.07.2026 (Tentative)
| Document Approval |  |  |  | QAP & Drawing Approval Pending
| Material Receive |  |  |  | Housing material Recived
| Machining |  |  |  | Done
6 | Fabrication Housing |  | 12-16 week for approval | 26.07.2026 (Tentative) | Legs, Lead & Nozzles Fabrication work are pending, will complete on 23.06.2026
| Hydro |  |  |  | 25.06.2026
| Rubber Lining |  |  |  | 18.07.2026
| Blasting Paintng |  |  |  | 19.07.026 To 21.07.2026
| Assembly |  |  |  | 22.07.2026 To 25.07.2026
| FAT |  |  |  | 22.07.2026 To 25.07.2026
7 | Thermax - 3.6K 02 Nos |  |  | 26.07.2026 (Tentative)
| Document Approval |  |  |  | QAP & Drawing Approval Pending
| Material Receive |  |  |  | Recived
| Machining |  |  |  | Done
| Fabrication Housing |  |  |  | only Lid Fabrication work are pending
| Hydro |  |  |  | 25.06.2026
| Rubber Lining |  |  |  | 18.07.2026
| Blasting Paintng |  |  |  | 19.07.026 To 21.07.2026
| Assembly |  |  |  | 22.07.2026 To 25.07.2026
| FAT |  |  |  | 22.07.2026 To 25.07.2026
| Thermax - 12K - 03 Nos |  |  | 26.07.2026 (Tentative)
| Document Approval |  |  |  | PO & Approved Drawing not Available
| Material Receive |  |  |  | Recived
| Machining |  |  |  | 13.06.2026
| Fabrication Housing |  |  |  | Will complete on 23.06.2026
| Hydro |  |  |  | 25.06.2026
| Rubber Lining |  |  |  | 18.07.2026
| Blasting & Paintng |  |  |  | 21.07.2026
| Assembly |  |  |  | 22.07.2026 To 25.07.2026
| FAT |  |  |  | 22.07.2026 To 25.07.2026
8 | Vasuki - Screen 10k EBS - 01 Nos | V/MI/0116, Dtd : 11/05/2026 | 10 Weeks | 19.06.2026
9 | Vasuki - Triton SLN 3.6K- 1 Nos | V/MI/0118, dtd : 23.04.2026 | 10 Weeks | 28.06.2026 | Approved Drawing not Available
| Document Approval |  |  |  | Done
| Material Receive |  |  |  | Screen, suction scanner & screen support, upper bearing wil recived on 20.06.2026
| Machining |  |  |  | Done
| Fabrication Housing |  |  |  | Done
Hydro
9 | Blasting & Paintng | V/MI/0118, dtd : 23.04.2026 | 10 Weeks | 28.06.2026
Assembly
FAT
10 | Hydro Flow - Export - 55" - 06 Nos | 00070361, Dtd : 15/05/2026 |  | 22.07.2026
| Document Approval |  |  |  | Pending
Media Filter : 6 Nos.
| Material Receive |  |  |  | Material Recived
| Rolling & Pressing |  |  |  | will recive on 20.06.2026
| Fabrication Housing |  |  |  | will complete on 04.07.2026
| Hydro |  |  |  | will complete on 06.07.2026
| Blasting & Paintng |  |  |  | will complete on 20.07.2026
| Manifold & Triton 7.2K |  |  |  | 02.07.2026 To 08.07.2026
| Assembly |  |  |  | 09.07.2026
| FAT |  |  |  | 09.07.2026
| Packing |  |  |  | 22.07.2026
11 | IHP Manifolds : 4 Set | 674, dtd : 20.03.2026 |  | 24.06.2026 | Under Facbrication & 16 Nos Flanges deliverd on 11.06.2026 & Balance 32 Nos delivery within 10 days
Elbow : 4 nos
Dismentalling Joint : 12 nos
inlet & Outlet Spool : 8 Nos
12 | IOCL - 1.2 Mtr Vessels | 396 dtd : 19.02.2025 | 6 Months
| Document Approval |  |  |  | Pending
13 | VTL : 26 set | 4600000225, dtd : 24.03.2026
Triton : 45K : 10nos
Triton : 60K : 13nos
Triton : 29K : 2nos
| Document Approval |  |  |  | Pending
14 | Leighton India
| Document Approval |  |  |  | Pending
15 | VISL | GEMC-511687702432980, DTD : 05.06.2026 | 05.07.2026 | 26.06.2026
Activated Filter Media
Gravels

## 24.04.2026 (2) (hidden)
Production Schedule : 11.06.2026 |  | PO. NO. & Date | Delivery Date | Fitter | Welder | Status | April | [29 empty] | May | [30 empty] | June | [26 empty] | Jully
. | Product Description | [5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 15 | 16 | 17 | 18 | 19 | 20 | 22 | 23 | 24 | 25 | 26 | 27 | 29 | 30 | 1 | 2 | 3 | 4 | 6 | 7 | 8 | 9 | 10 | 11 | 13 | 14 | 15 | 16 | 17 | 18 | 20 | 21 | 22 | 23 | 24 | 25 | 27 | 28 | 29 | 30
1 | Priyanjas - Container Systems | PJ/YWSPL/020-R1/25-26 DTD : 10.06.2025 | 10-12 Week
| Laminar setllar 2 nos & Storge Tank : 2 Nos |  |  |  |  | Fabrication Done & Painting & Leakge test pending
| Container Body |  |  |  |  | Waiting for further clearance
2 | JSW Dolvi - 12K SLN - 01 Nos |  |  |  |  | Ready for Dispatch
3 | JSPL Angul 3 Mtr - Vessel Systems
| Media Filter |  | 18.06.2026 |  |  | Under Painting
Manifold
| Valve |  |  |  |  | Recived
| Compressor |  |  |  |  | Received
| Panel |  |  |  |  | Received
| Fastners |  |  |  |  | Received
| Media & Gravers |  |  |  |  | on 12.06.206 will recived
| Lateral |  |  |  |  | 15.06.2026 will recived in our premises
| Backwash Pump |  |  |  |  | on 13.06.206 will recived
| Lateral Header Pipe |  |  |  |  | on 13.06.206 Will ready
4 | Rashmi Metal - 18K - 02 Nos | 30.03.2026 | 30.06.2026 |  |  | Fitter - Pramod Gupta
| Screen |  | 12.06.2026 |  |  | Today will recive
| FAT |  |  |  |  | Today will perform
5 | Ion Exchange 18K - 2 nos | 4100011453, Dtd : 19.04.2026 | 25.06.2026
| Document Approval Required |  |  |  |  | Done
| Material Receive |  |  |  |  | Done
| Machining |  |  |  |  | One set is reday only painting & assembly pending Housing material wil recived on 13.06.2026
| Fabrication Housing |  |  |  |  | 17.06.2026 machining will done (SR Engg Work)
| Hydro |  |  |  |  | 21.06.2026
| Blasting Paintng |  |  |  |  | 24.06.2026
| Assembly |  |  |  |  | 25.06.2026
| FAT |  |  |  |  | 25.06.2026
6 | Thermax - 7.2K 03 Nos |  | 12-16 week for approval
| Document Approval Required |  |  |  |  | QAP & Drawing Approval Pending
| Material Receive |  |  |  |  | Housing material Recived
| Machining |  |  |  |  | Done
| Fabrication Housing |  |  |  |  | Legs, Lead & Nozzles Fabrication work are pending, will complete on 13.06.2026
Hydro
Rubber Lining
Blasting Paintng
Assembly
FAT
7 | Thermax - 3.6K 02 Nos
| Document Approval Required |  |  |  |  | QAP & Drawing Approval Pending
| Material Receive |  |  |  |  | Recived
| Machining |  |  |  |  | Done
| Fabrication Housing |  |  |  |  | only Lid Fabrication work are pending
Hydro
Rubber Lining
Blasting Paintng
Assembly
FAT
7 | Thermax - 12K - 03 Nos
| Document Approval Required |  |  |  |  | PO & Approved Drawing not Available
| Material Receive |  |  |  |  | Recived
| Machining |  |  |  |  | 13.06.2026
Fabrication Housing
Hydro
Rubber Lining
Blasting & Paintng
Assembly
FAT
8 | Vasuki - Screen 10k EBS - 01 Nos | V/MI/0116, Dtd : 11/05/2026 | 19.06.2026
9 | Vasuki - Triton SLN 3.6K- 1 Nos | 23.04.2026 | 28.06.2026 |  |  | Approved Drawing not Available
| Document Approval Required |  |  |  |  | Done
| Material Receive |  |  |  |  | Screen, suction scanner & screen support, upper bearing wil recived on 20.06.2026
| Machining |  |  |  |  | Done
| Fabrication Housing |  |  |  |  | Done
Hydro
Blasting & Paintng
Assembly
FAT
10 | Hydro Flow - Export - 55" - 06 Nos | 00070361, Dtd : 15/05/2026 | 10.07.2026 |  |  | Drawing Approval Required
| Document Approval Required |  |  |  |  | Pending
Media Filter : 6 Nos.
| Material Receive |  |  |  |  | Recived
| Rolling & Pressing |  |  |  |  | will recive on 20.06.2026
| Fabrication Housing |  |  |  |  | will complete on 04.07.2026
| Hydro |  |  |  |  | will complete on 06.07.2026
| Blasting & Paintng |  |  |  |  | will complete on 20.07.2026
| Manifold & Triton 7.2K |  |  |  |  | 02.07.2026 To 08.07.2026
| Assembly |  |  |  |  | 09.07.2026
| FAT |  |  |  |  | 09.07.2026
| Packing |  |  |  |  | 22.07.2026
11 | IHP Manifolds : 4 Set | 674, dtd : 20.03.2026 | 24.06.2026
| Elbow : 4 nos |  |  |  |  | Under Facbrication & 16 Nos Flanges deliverd on 11.06.2026 & Balance 32 Nos delivery within 10 days
Dismentalling Joint : 12 nos
inlet & Outlet Spool : 8 Nos
12 | IOCL - 1.2 Mtr Vessels | 396 dtd : 19.02.2025
| Document Approval |  |  |  |  | Pending
13 | VTL : 26 set | 4600000225, dtd : 24.03.2026
Triton : 45K : 10nos
Triton : 60K : 13nos
Triton : 29K : 2nos
| Document Approval |  |  |  |  | Pending
14 | Leighton India
| Document Approval |  |  |  |  | Pending